## QA Log
Log ID | Site Code | Date | Stage | Check Item | Result | Evidence Ref | Remarks
QA-0001 | SITE-A | 2025-01-10 | Pre | Materials complete | PASS | PHOTO-SET-A | Counts verified; no serials captured
QA-0002 | SITE-A | 2025-01-10 | Pre | Sky visibility | PASS | APP-SCAN-A | No obstruction detected
QA-0003 | SITE-A | 2025-01-10 | During | Mount stability | PASS | PHOTO-MOUNT-A | Torque check completed
QA-0004 | SITE-A | 2025-01-10 | During | Wiring polarity | PASS | METER-READ-A | Verified before energizing
QA-0005 | SITE-A | 2025-01-10 | Post | Speed test | PASS | TEST-A-01 | 128/18 Mbps; 29 ms
QA-0006 | SITE-B | 2025-01-15 | Pre | Site readiness | PASS | PHOTO-SITE-B | Mount location approved
QA-0007 | SITE-B | 2025-01-15 | During | Cable management | PASS | PHOTO-CABLE-B | Conduit + drip loop installed
QA-0008 | SITE-B | 2025-01-15 | Post | Voltage stability | PASS | METER-READ-B | 12.6V to 12.9V stable
QA-0009 | SITE-C | 2025-01-20 | Pre | Materials complete | PASS | CHECKLIST-C | Spare fuse included
QA-0010 | SITE-C | 2025-01-20 | Post | Documentation audit | PASS | FOLDER-AUDIT-C | All forms uploaded

## QC Log
QC ID | Site Code | Date | Inspection Item | Acceptance Criteria | Status | Corrective Action | Final Result
QC-0001 | SITE-A | 2025-01-10 | Dish mounting | No movement | PASS | N/A | ACCEPTED
QC-0002 | SITE-A | 2025-01-10 | Weatherproofing | Sealed entries | PASS | N/A | ACCEPTED
QC-0003 | SITE-A | 2025-01-10 | Speed test | Download >= 50 Mbps | PASS | N/A | ACCEPTED
QC-0004 | SITE-B | 2025-01-15 | Solar mounting | Firm; no shading | PASS | N/A | ACCEPTED
QC-0005 | SITE-B | 2025-01-15 | Polarity check | Correct | PASS | N/A | ACCEPTED
QC-0006 | SITE-B | 2025-01-15 | Latency | <= 60 ms | PASS | N/A | ACCEPTED
QC-0007 | SITE-C | 2025-01-20 | Documentation | Complete; privacy-safe | PASS | N/A | ACCEPTED
QC-0008 | SITE-C | 2025-01-20 | Battery voltage | Within range | PASS | N/A | ACCEPTED
QC-0009 | SITE-C | 2025-01-20 | Cable routing | Secured | PASS | N/A | ACCEPTED
QC-0010 | SITE-C | 2025-01-20 | Grounding | Bonded properly | PASS | N/A | ACCEPTED